## Project
PROJECT TRACKING TEMPLATE
Project name: | Acne studios website build | Manager: | Jon Snow
Scope document link: | link | Over / under | 2700
Hourly rate | 150 | Progress |  |  |  |  | 57.14%
Task name |  | Assigned to | Status | Start date | End date | Estimated hours | Estimated cost | Actual hours | Actual cost | Over / under
Task 1 |  | Bradley | Done | 2022-11-09 | 2022-11-30 | 4 | 600 | 5 | 750 | -150
Task 2 |  | Derek | Done | 2022-11-10 | 2022-12-01 | 6 | 900 | 5 | 750 | 150
Task 3 |  | Anna | Done | 2022-11-11 | 2022-12-02 | 6 | 900 | 0 | 0 | 900
Task 4 |  | Cecile | To do | 2022-11-29 | 2022-11-23 | 12 | 1800 | 0 | 0 | 1800
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0

## Tracker
PROJECT TRACKER TEMPLATE
Task name | Hours worked | Reported by | On date
Task 1 | 2 | Bradley | 2022-11-01
Task 1 | 3 | Anna | 2022-11-03
Task 2 | 5 | Cecile | 2022-11-07

## Master
Team | Status | Working hours/Day
Anna | To do | 8
Bradley | In progress
Cecile | Done
Derek | To do
Emma